## UAT Phase 13-16
User Acceptance Test (UAT) - Puti Internship Management System (Premium Edition) - V2.0
No. Dokumen: 1516/QA-PuTi/RUNDOWN-UAT/V2/2026
Tanggal: 12 Februari 2026
Environment: http://localhost:3001 (Production Mode)
Tim Penguji: QA Team / Project Lead
No | Modul/Menu | Test Case | Langkah Testing | Expected Result | Status | Actual Result
PHASE 13
1 | Registration Form | Create New Form | 1. Login Admin 2. Akses /ManagementData -> Tab Registration 3. Klik "Create New Form" 4. Isi Judul, Deskripsi, Field 5. Simpan | Form baru berhasil dibuat dan status Active. | Done | Done
2 | Registration Form | Dynamic Slug Generation | 1. Ketik Judul Form 2. Cek field "URL Slug" 3. Edit manual jika perlu | URL Slug otomatis ter-generate dan bisa diedit. | Done | Done
3 | Registration Form | Toggle Active Status | 1. Cari form aktif 2. Toggle Switch "Active" 3. Konfirmasi | Status form berubah jadi Inactive. | Done | Done
4 | Registration Form | Edit Existing Form | 1. Klik icon "Edit" 2. Ubah data 3. Simpan | Perubahan tersimpan dan update di publik. | Done | Done
5 | Registration Form | Delete Form | 1. Klik icon "Delete" 2. Konfirmasi | Form terhapus permanen. | Done | Done
PHASE 14
6 | Public Portal | Access Job Listing | 1. Logout / Incognito 2. Akses /registration 3. Lihat list | Tampil daftar lowongan aktif tanpa login. | Done | Done
7 | Public Portal | View Form Details | 1. Klik lowongan 2. Verifikasi loading | Halaman detail form terbuka sesuai slug. | Done | Done
8 | Submission | Submit Application | 1. Isi field wajib 2. Klik Submit | Data terkirim, muncul Thank You page + ID. | Done | Done
9 | Submission | Validation Check | 1. Kosongkan field wajib 2. Submit | Error validasi muncul, submit ditolak. | Done | Done
PHASE 15
10 | Applications | View Submissions List | 1. Login Admin 2. Akses /Applications | Tabel menampilkan pelamar masuk. | Done | Done
11 | Applications | Filtering & Search | 1. Cari nama 2. Filter status | Tabel memfilter data real-time. | Done | Done
12 | Applications | Application Review | 1. Klik View pelamar Pending 2. Cek jawaban | Detail jawaban form muncul di popup. | Done | Done
13 | Applications | Approval Workflow | 1. Klik Approve/Reject 2. Konfirmasi | Status berubah sesuai tindakan. | Done | Done
PHASE 16
14 | Database | PostgreSQL Sync | 1. Cek tabel via Script | Data tersimpan dengan relasi valid. | Done | Done
15 | Security | Public API Protection | 1. Akses API invalid payload | Return error 400/404. | Done | Done
Approval:
Role | Name | Signature | Date
Project Manager | [Nama PM] | ___________________ | 12 Feb 2026
QA Lead | [Nama QA] | ___________________ | 12 Feb 2026